## Sheet1
User | Module / Session | Start Date | End Date | Status | Notes
Shubham | Module 1: JavaScript Refresher | 2025-04-01 | 2025-04-05 | ✅ Completed | Quick learner, aced callbacks
| Module 1: React Basics | 2025-04-06 | 2025-04-10 | ✅ Completed | Clear with props/state
| Module 1: Styling in React | 2025-04-11 | 2025-04-14 | 🟡 In Progress | Needs help with Tailwind
| Module 1: React – A Deeper Dive | 2025-04-15 | 2025-04-17 | ⏳ Not Started
| 🔁 Review Session 1 |  |  | ⏳ Not Started | Schedule recap & quiz on Module 1
| Module 2: Forms & Validation |  |  | ⏳ Not Started | Scheduled next week
| Module 2: REST APIs in React |  |  | ⏳ Not Started
| Module 2: Graphs & Charts |  |  | ⏳ Not Started
| 🔁 Review Session 2 |  |  | ⏳ Not Started | Focus on form validation & APIs
| Module 3: Deploying a React App |  |  | ⏳ Not Started
| Module 3: Final Assignments |  |  | ⏳ Not Started | Project demo & feedback
| 🔁 Review Session 3 (Optional) |  |  | ⏳ Not Started
Suyash | Module 1: JavaScript Refresher | 2025-04-02 | 2025-04-06 | ✅ Completed | Needed 1 extra day for async
| Module 1: React Basics | 2025-04-07 | 2025-04-12 | ✅ Completed | Smooth progress
| Module 1: Styling in React | 2025-04-13 | 2025-04-15 | 🟡 In Progress | Starting Tailwind
| Module 1: React – A Deeper Dive | 2025-04-16 |  | ⏳ Not Started
| 🔁 Review Session 1 |  |  | ⏳ Not Started | Book for 2025-04-18
| Module 2: Forms & Validation |  |  | ⏳ Not Started
| Module 2: REST APIs in React |  |  | ⏳ Not Started
| Module 2: Graphs & Charts |  |  | ⏳ Not Started
| 🔁 Review Session 2 |  |  | ⏳ Not Started | Use previous quiz template
| Module 3: Deploying a React App |  |  | ❌ Skipped
| Module 3: Final Assignments |  |  | ⏳ Not Started | Will cover later if needed
| 🔁 Review Session 3 (Optional) |  |  | ⏳ Not Started